## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2 | done
1.1 | crud for ssc form and jest | 6 | ziad/abdoh | karim | ahmed mustafa | yes
1.2
1.3
1.4 | As an investor I can track my case of my request. /jest | 1 | nabil | essam | saleh | yes
1.5
1.6 | As a lawyer I can generate pdf contract /jest | 3 | ziad | yara | osama | yes
1.7 | As a lawyer I can review the form so that I decide if it has invalid information. /jest | 2 | osama | saleh | rawda | no
1.8 | As a lawyer I can show comments of the reviewer in case of rejection. /jest | 1 | nabil | essam | ziad | yes
1.9 | .As a lawyer I can show my tasks I have /jest | 2 | saleh | osama | rawda | no
2 | .As a lawyer I can show my tasks (in basket) so that I can access any case /jest | 3 | essam | nabil | ziad | yes
2.1 | As a lawyer I can show my tasks details. /jest | 1 | abdoh | ahmed mustafa | nabil | yes
2.2 | As a lawyer I can calculate the fees /jest | 2 | abdoh | ashraf | yara | yes
2.3 | As a lawyer I can recalculate fees after editing the form /jest | 1 | rawda | saleh | osama | yes
2.4 | As a reviewer I can review the form so that I decide if it is accepted or not. /jest | 2 | essam | nabil | yara | yes
2.5 | As a reviewer I can comment on rejected cases. /jest | 1 | ahmed mustafa | karim | ziad | no
2.6 | As an admin I can show all cases. /jest | 3 | nabil | essam | abdoh | yes
2.7 | As an admin I can view case details. /jest | 1 | karim | ahmed mustafa | ziad | no
2.8
2.9 | jest for investor | 5 | rawda | ashraf | saleh | yes
3 | jest for lawyer | 5 | yara | abdoh | karim | yes
3.1 | jest for reviewer | 5 | ahmed mustafa | karim | nabil | yes
3.2 | jest for admin | 5 | ashraf | rawda | osama | yes
3.3 | jest for company | 5 | karim | ahmed mustafa | yara | yes
3.4 | jest for spc form | 5 | saleh/osama | rawda | abdoh | yes
3.5 | as a laywer I should initiate payment /jest | 1 | ziad | rawda | saleh | yes
3.6 | as an investorr I shoukd be able to make a payment /jest | 1 | ziad | ossama | abdoh | yes
3.7
3.8 | login and register for investor | 3 | rawda | saleh | ashraf | yes
3.9 | login and register for laywer | 3 | abdoh |  |  | yes