## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | investor
1.1 | create | 2 | rawda |  | Yes for all via local host and arrays
1.2 | read | 1 | yara |  | Yes for all via local host and arrays
1.3 | update | 3 | yara | create | Yes for all via local host and arrays
1.4 | delete | 3 | rawda | create | Yes for all via local host and arrays
2 | laywer
2.1 | create | 2 | karim |  | Yes for all via local host and arrays
2.2 | read | 1 | karim |  | Yes for all via local host and arrays
2.3 | update | 3 | ahmed | create | Yes for all via local host and arrays
2.4 | delete | 3 | ahmed | create | Yes for all via local host and arrays
3 | reviewer
3.1 | create | 2 | mohamed saleh |  | Yes for all via local host and arrays
3.2 | read | 1 | ossama |  | Yes for all via local host and arrays
3.3 | update | 3 | assama | create | Yes for all via local host and arrays
3.4 | delete | 3 | moahmed saleh | create | Yes for all via local host and arrays
4 | admin
4.1 | create | 2 | ziad |  | Yes for all via local host and arrays
4.2 | read | 1 | ziad |  | Yes for all via local host and arrays
4.3 | update | 3 | Abdulrahman | create | Yes for all via local host and arrays
4.4 | delete | 3 | moahamed ashraf | create | Yes for all via local host and arrays
5 | Company
5.1 | create | 2 | Mohammad Essam |  | Yes for all via local host and arrays
5.2 | read | 1 | Nabil Samy |  | Yes for all via local host and arrays
5.3 | update | 3 | Nabil Samy | create | Yes for all via local host and arrays
5.4 | delete | 3 | Mohammad Essam | create | Yes for all via local host and arrays