## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1.1 | crud for ssc form and mongose &JOI | 6 | ziad/abdoh | karim | ahmed mustafa
1.2 | crud for spc form and mongose&JOI | 6 | saleh/osama | rawda | abdoh
1.3
1.4 | As an investor I can track my case of my request. | 1 | nabil | essam | saleh
1.5
1.6 | As a lawyer I can generate pdf contract | 3 | ziad | yara | osama
1.7 | As a lawyer I can review the form so that I decide if it has invalid information. | 2 | osama | saleh | rawda
1.8 | As a lawyer I can show comments of the reviewer in case of rejection. | 1 | nabil | essam | ziad
1.9 | .As a lawyer I can show my tasks I have | 2 | saleh | osama | rawda
2 | .As a lawyer I can show my tasks (in basket) so that I can access any case | 3 | essam | nabil | ziad
2.1 | As a lawyer I can show my tasks details. | 1 | abdoh | ahmed mustafa | nabil
2.2 | As a lawyer I can calculate the fees. | 2 | abdoh | mohamad ashraf | yara
2.3 | As a lawyer I can recalculate fees after editing the form | 1 | rawda | saleh | osama
2.4 | As a reviewer I can review the form so that I decide if it is accepted or not. | 2 | essam | nabil | yara
2.5 | As a reviewer I can comment on rejected cases. | 1 | ahmed mustafa | karim | ziad
2.6 | As an admin I can show all cases. | 3 | nabil | essam | abdoh
2.7 | As an admin I can view case details. | 1 | karim | ahmed mustafa | ziad
2.8
2.9 | mongose for investor&JOI | 5 | rawda | mohamad ashraf | saleh
3 | mongose for lawyer&JOI | 5 | yara | abdoh | karim
3.1 | mongose for reviewer&JOI | 5 | ahmed mustafa | karim | nabil
3.2 | mongose for admin&JOI | 5 | mohamad ashraf | rawda | osama
3.3 | mongose for company&JOI | 5 | karim | ahmed mustafa | yara