## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1.1 | As An Investor I can register an account | 8 | Rawda | karim | ahmed mustafa
1.2 | As An Admin, I can recruite Reviewer | 8 | Ahmed Mustafa | rawda | abdoh
1.3 | As An Admin, I can recruite Other Admins | 8 | Ashraf | Ziad | Rawda
1.4 | As An Admin, I can recruite Lawyers | 8 | Abdo | essam | saleh
1.5 | As An Admin, I can Delete Lawyers | 5 | Yara | Nabil | Karim
1.6 | As An Admin, I can Delete Reviewers | 5 | Ahmed Mustafa | Essam | abdoh
1.8 | As An Admin I can update Reviewres Account Details | 5 | Ahmed Mustafa | Ziad | Karim
1.9 | As An Admin I can update Lawyers Account Details | 5 | Abdo | Saleh | Yara
2 | As An Admin I can update My Account Details | 5 | Ashraf | Saleh | Osama
2.1 | As An Investor I can Delete my Account | 5 | Rawda | Saleh | Osama
2.2 | As An Admin, I can Delete departng Admins | 5 | Ashraf | yara | osama
2.3 | As a lawyer I can review the form so that I decide if it has invalid information. | 3 | Ziad | saleh | rawda
2.4 | As a lawyer I can show comments of the reviewer in case of rejection. | 5 | Saleh | essam | ziad
2.5 | As an Admin I can add finalized companies to the system | 8 | Karim | osama | rawda
2.6 | As an Admin I can update info about companies | 5 | Karim | Ziad | ahmed mustafa
2.7 | As an Admin I can delete companies that are no longer in business | 5 | Karim | Ziad | Ashraf
2.8 | As An investor I can view registerd companies | 2 | Karim | nabil | ziad
2.9 | As An Investor I can apply for SSC companies ownership | 8 | Ziad | ahmed mustafa | nabil
3 | As An Investor I can apply for SPC companies ownership | 8 | Saleh | ashraf | yara
3.1 | As an Investor I can update my SPC form incase of rejection or mistakes | 5 | Osama | Saleh | Yara
3.2 | As an Investor I can update my SSC form incase of rejection or mistakes | 5 | Essam | saleh | osama
3.4 | As An Investor, I can update my account details. | 5 | Rawda | karim | ziad
3.5 | As an admin I can show all cases. | 8 | Ashraf | essam | abdoh
3.6 | As an admin I can view case details. | 5 | Essam | Yara | Ashraf
3.7 | As an Admin I can show all lawyers | 5 | Nabil | Essam | Osama
3.8 | As a lawyer I can pass or not pass cases | 5 | Nabil | ashraf | Yara
1900-01-03 | As an Admin I can show all Investros | 5 | Rawda | Yara | Karim
4.1 | As an investor I can Track my case/ get copy of my contract | 2 | Ziad | karim | Abdoh
4.2 | As a lawyer I should get a copy of the contract | 2 | Ziad | Ashraf | Saleh