## Sheet1
1 | As an investor I can apply for SSC Form (React FrontEnd) | 2 | ziad | karim | ahmed mustafa | yes
1.2 | As a lawyer I can generate pdf contract (REACT FrontEnd) | 1 | ziad | yara | osama | yes
1.3 | As a lawyer I can review the form so that I decide if it has invalid information. (REACT FrontEnd) | 2 | osama | saleh | rawda | yes
1.4 | As a lawyer I can show comments of the reviewer in case of rejection. (REACT FrontEnd) | 2 | Nabil | essam | abdoh | yes
1.5 | .As a lawyer I can show my tasks (in basket) so that I can access any case (REACT FrontEnd) | 3 | essam | nabil | ziad | yes
2 | As a lawyer I can show my tasks details. (REACT FrontEnd) ToBeCancaled as Abdo already has 1 story | 1 | abdoh | ahmed mustafa | nabil | yes
2.1 | As a lawyer I can calculate the fees (REACT FrontEnd) ToBeCancale as Abdo already has 1 story | 2 | abdoh | ashraf | yara | yes
2.2 | As a lawyer I can recalculate fees after editing the form (REACT FrontEnd) | 1 | rawda | saleh | osama | yes
2.3 | As a reviewer I can review the form so that I decide if it is accepted or not. (REACT FrontEnd) | 2 | essam | nabil | yara | yes
2.4 | As a reviewer I can comment on rejected cases. (REACT FrontEnd) | 1 | ahmed mustafa | karim | ziad | no
2.5 | As an admin I can show all cases. (REACT FrontEnd) | 3 | nabil | essam | abdoh | yes
2.6 | As an admin I can view case details. (REACT FrontEnd) | 3 | karim | ahmed mustafa | ziad | no
3 | Searching for specific Admin using Search Bar(React Front-end) | 3 | Ashraf | saleh | Rawda | yes
3.1 | login and register for laywer (React FrontEnd) | 3 | abdoh | Ashraf | ahmed mustafa | yes
3.2 | As an investor I can apply for SPC Form (React FrontEnd) | 3 | Saleh | Ziad | Karim | yes
3.3 | As an Admin I should be able to delete SPC's | 1 | Saleh | ahmed mustafa | Ziad
3.5 | As a lawyer I should be able to view SPC's(form)/(React) | 1 | Saleh | nabil | Rawda
3.6 | As a lawyer I should be able to Edit SSC's(form)/(React) | 2 | Saleh | yara | osama
3.7 | As an Admin I should be able to delete SSC's(form)/(React) | 1 | Ziad | Saleh | Ashraf
3.8 | As a lawyer I should be able to view SSC's(form)/(React) | 1 | Ziad | Abdo | yara
3.9 | As a lawyer I should be able to Edit SSC's (form)/(React) | 2 | Ziad | Osama | Saleh
4 | Login and register for investor (front end react) | 3 | rawda | Ashraf | Saleh | no
Numbered | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2 | done